## Sheet1
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Province, City or Municipality: | ILOILO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extension, If any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Construction/Rehabilitation of Multi-Purpose Hall | Brgy. Libertad, Lapuz, Iloilo City | 1500000 | [5 empty] | Supplemental Budget #2, CY 2017
Installation of Street Lighting System | City Wide | [6 empty] | Supplemental Budget #2, CY 2017
-Zamora Extension, City Proper |  | 153936
-Valeria Street, City Proper |  | 415826
-Veterans Village, City Proper |  | 189006
-Iznart Extension & Magsaysay, City Proper |  | 267346
-Pepita Aquino, City Proper |  | 189006
-Fort San Pedro Drive, City Proper |  | 415826
-Ma. Clara, City Proper |  | 153936
-Blumentritt & Legaspi Sts., City Proper |  | 189006
-Delgado Street, City Proper |  | 521036
-Ortiz Street, City Proper |  | 153936
-Solis & Yulo Street, City Proper |  | 153936
-Muelle Loney Street, City Proper |  | 302416
-Arroyo & Arsenal Sts., City Proper |  | 189006
-Aldeguer & Guanco Sts., City Proper |  | 118866
-Fuentes Street, City Proper |  | 162136
-Rizal Estanzuela, City Proper |  | 83796
-Quezon Street, City Proper |  | 232276
-Rizal Street, City Proper |  | 521036
-San Juan, Molo, Iloilo City |  | 267346
-Baluarte St., Molo, Iloilo City |  | 521036
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Province, City or Municipality: | ILOILO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extension, If any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Installation of Street Lighting System | City Wide | [6 empty] | Supplemental Budget #2, CY 2017
-Brgy. Boulevard, Molo, Iloilo City |  | 189006
-Brgy. San Pedro, Molo, Iloilo City |  | 267346
-Brgy. Calumpang, Molo, Iloilo City |  | 289799
-Brgy. Tap-oc, Molo, Iloilo City |  | 157518
-Duran Street, City Proper |  | 189006
-Jalandoni Street, Iloilo City |  | 232276
-Gen. Luna St.(sidewalk), Iloilo City |  | 415826
-Gen. Hughes, City Proper |  | 267346
-Sto. Rosario Street, City Proper |  | 415826
-De Leon Street, City Proper |  | 267346
-Ybiernas Street, City Proper |  | 337486
-Bonifacio-Tanza, City Proper |  | 83796
-Rizal Pala-Pala I & II, City Proper |  | 153936
-Aduana Street, City Proper |  | 118866
-Zamora Street, City Proper |  | 153936
-Dela Rama Street, City Proper |  | 337486
-Mabini Street, City Proper |  | 232276
-Gomez Streeet, City Proper |  | 153936
-Burgos Street, City Proper |  | 83796
=San Agustin Street, City Proper |  | 118866
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Province, City or Municipality: | ILOILO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extension, If any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
SOCIAL DEVELOPMENT
Installation of Solar Street Lighting System | City Wide | [6 empty] | Realigned Resolution No. 6, S. 2017, dtd. 6/6/17
-Brgy. Boulevard, Molo, Iloilo City |  | 688000
-Brgy. Sinikway, Lapuz, Iloilo City |  | 3008000
-Brgy. Calaparan, Arevalo, Iloilo City |  | 3440000
-Brgy. North Baluarte, Molo, Iloilo City |  | 736000
-Brgy. Bito-on, Jaro, Iloilo City |  | 2544000
-Brgy. North San Jose, Molo, Iloilo City |  | 304000
-Brgy. Dungon C, Mandurriao, Iloilo City |  | 1280000
Improvement of Brgy. Health Center thru Provision of Medical Equipment | City Wide | 1500000 | [5 empty] | Annual Budget, CY 2017
Improvement of Brgy. Health Center thru Provision of Medical Equipment | City Wide | 999975 | [5 empty] | Annual Budget, CY 2017
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| NINDA D. ATINADO |  |  |  | JOSE S. ESPINOSA III
| Budget Officer |  |  |  | City Mayor
Source: 20% Development Fund
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Province, City or Municipality: | ILOILO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extension, If any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
LOAN AMORTIZATION - July - September 2017 | DBP - SOLID WASTE MANAGEMENT | 1867176.59 | [5 empty] | Principal loan of the 89M loan of the Iloilo City Gov't. to Dev't. Bank of the Philippines
NHA LOAN AMORTIZATION - July - September 2017 | ACQUISITION OF A RESETTLEMENT SITE FOR HOUSING DEVELOPMENT | 1451625 | [5 empty] | Payment of monthly Amortization to National Housing Authority for the acquisition of a resettlement site for housing dev't. under the Poverty Alleviation Funds(PAF3)
NHA LOAN AMORTIZATION - July - September 2017 | INFRASTRUCTURE PROJECTS AT SAN ISIDRO RESETTLEMENT SITE | 177825 | [5 empty] | Payment of Monthly . Amortization to National Housing Authority for the Infrastructure projects at San Isidro Resettlement Site.
LOAN AMORTIZATION | DBP - SANITARY LANDFILL PROJECT | 6059708.48 | [5 empty] | Payment of Principal for the Loan of Iloilo City Government to DBP under the Sanitaty Landfill Project.
Repair of Footbridge | Brgy. West Habog-Habog, Molo, Iloilo City | 1000000 | [5 empty] | Annual Budget 2017
Rehabilitation/Construction of Public Alley | Brgy. Railway, Lapaz, Iloilo City | 800000 | [5 empty] | Annual Budget 2017
Rehabilitation/Construction of Roads | Brgy. Yulo Drive, Arevalo, Iloilo City | 2000000 | [5 empty] | Annual Budget 2017
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Province, City or Municipality: | ILOILO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extension, If any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
ECONOMIC DEVELOPMENT
Construction/Repair of Toilet | Jaro Big Market, Jaro, Iloilo City | 630000 | [5 empty] | Supplemental Budget #2, CY 2017
Construction/Repair of Toilet | Lapaz Market, Lapaz, Iloilo City | 1620000 | [5 empty] | Supplemental Budget #2, CY 2017
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of the data or information contained in this document.
| NINDA D. ATINADO |  |  |  | JOSE S. ESPINOSA
| Budget Officer |  |  |  | City Mayor
Source:
20% Development Fund, CY 2017
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
FOR THE 4th QUARTER, CY 2017
Province, City or Municipality: | ILOILO CITY
Program or Project | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extension, If any | Remarks
[5 empty] | % of Completion | Total Cost Incurred to Date
ENVIRONMENTAL MANAGEMENT
Construction/Rehabilitation of Existing Drainage System | Brgy. Navais, Mandurriao, Iloilo City | 5000000 | [5 empty] | Annual Budget 2017
Construction/Rehabilitation of Existing Drainage System | Brgy. PHHC Block 17, Mandurriao, Iloilo City | 1000000 | [5 empty] | Annual Budget 2017
| NINDA D. ATINADO |  |  |  | JOSE S. ESPINOSA III
| Budget Officer |  |  |  | City Mayor
Source:
20% Development Fund, CY 2017